## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
My diagram isn't correct | 2 | 8 | 16 | 2021-04-02 | Migated | M | Verified with the professor
My planning doc gets deleted | 1 | 20 | 40 | 2021-04-02 | Migated | M | Uploaded to Cloud
The physics require differential equations | 5 | 100 | 500 | 2021-04-08 | Migated | M | The professor said wasn't required
Not certain on if my write up is correct | 20 | 100 | 2000 | 2021-04-09 | Accepted | A | Already turned in week 1, about to turn in week 2
Redo Physics Unit tests | 70 | 5 | 350 | 2021-04-09 | Accepted | A | Hard to know physics function implemention to have a completely accurate unit test
Writing Physics Equations | 70 | 40 | 2800 | 2021-04-09 | Owned | O | Equations are not finalized so, no solution yet
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100