## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
My diagram isn't correct | 2 | 8 | 16 | 2021-04-02 | Migated | M | Verified with the professor
My planning doc gets deleted | 1 | 20 | 40 | 2021-04-02 | Migated | M | Uploaded to Cloud
The physics require differential equations | 1 | 100 | 100 | 2021-04-08 | Migated | M | The professor said wasn't required
Not certain on if my write up is correct | 1 | 70 | 70 | 2021-04-09 | Accepted | A | Got a good grade so this is no longer a huge risk
Redo Physics Unit tests | 100 | 20 | 2000 | 2021-04-09 | Accepted | A | Physics engine is proving difficult unit tests will need more iteration
Writing Physics Equations | 100 | 70 | 7000 | 2021-04-09 | Owned | O | Equations still aren't finalized
LCD Task hasn't been started | 40 | 40 | 1600 | 2021-04-16 | Accepted | A | Others are having issues drawing on lcd, haven't looked into it yet
Speed of game | 20 | 13 | 260 | 2021-04-16 | Accepted | A | Haven't gotten far enough to check the speed of the physics task
0
0
0
0
0
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100