## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
My diagram isn't correct | 1 | 8 | 16 | 2021-04-02 | Migated | M | Verified with the professor
My planning doc gets deleted | 1 | 20 | 40 | 2021-04-02 | Migated | M | Uploaded to Cloud
The physics require differential equations | 1 | 100 | 100 | 2021-04-08 | Migated | M | The professor said wasn't required
Not certain on if my write up is correct | 1 | 70 | 70 | 2021-04-09 | Accepted | A | Got a good grade so this is no longer a huge risk
Redo Physics Unit tests | 1 | 1 | 1 | 2021-04-09 | Resolved | A | Physics engine has been finished and is getting the correct outputs
Writing Physics Equations | 1 | 1 | 1 | 2021-04-09 | Resolved | A | Equations are finalized
LCD Task is in progress | 1 | 40 | 40 | 2021-04-16 | Resolved | A | Display task is finished and working great
Speed of game | 1 | 13 | 13 | 2021-04-16 | Accepted | A | Game speed is not an issue
Messages Queue output to LCD from Physics engine | 1 | 40 | 40 | 2021-04-23 | Accepted | A | The LCD takes data from physics task and displays it correctly
0
0
0
0
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100